## Traceability Matrix
TRACEABILITY MATRIX
Practice Software Testing – Functional, UI, API & Performance Testing Coverage
Project | Practice Software Testing
Document | Traceability Matrix
Purpose | Trace requirements to test scenarios/cases and execution evidence.
Testing Scope | Functional / Manual UI / UI Automation / API / Performance
Status | Ready for execution update
Req ID | Requirement / Feature | Test Level | Test Type | Test Scenario / Coverage | Automation Status | Execution Status | Evidence / Reference
REQ-UI-001 | Application availability / home page | UI | Functional / Smoke | Verify application opens successfully and returns a valid response. | Automated | Passed | k6 UI smoke result / Playwright UI smoke
REQ-UI-002 | Product listing | UI | Functional | Verify products page loads and displays product data correctly. | Automated / Manual | Blocked – data | Products endpoint currently returns empty dataset; DB product count = 0.
REQ-UI-003 | User authentication | UI | Functional / Regression | Verify valid login, invalid login, logout and session behavior. | Automated | Pending | Playwright UI test suite
REQ-UI-004 | Product browsing / search | UI | Functional / Regression | Verify product navigation, search, filtering and product detail access. | Automated | Pending | Playwright UI test suite
REQ-API-001 | API health/status | API | Functional / Smoke | Verify API status endpoint returns HTTP 200 and expected environment/application information. | Automated | Passed | curl.exe /status
REQ-API-002 | Product API | API | Functional | Verify GET products returns valid response structure and expected product records. | Automated | Blocked – data | GET /products returns 200 with empty data because products table contains 0 records.
REQ-API-003 | Authentication API | API | Security / Functional | Verify authenticated and unauthenticated access behavior, including invalid/expired token scenarios where applicable. | Automated | Pending | Playwright API test suite
REQ-API-004 | Invoice API | API | Functional / Security | Verify invoice retrieval for valid ID, invalid ID, another user's ID, missing token and expired token. | Automated | Executed | API test cases / screenshots / reports
REQ-API-005 | Error handling | API | Negative | Verify API returns appropriate error response for invalid input, missing resources and server-side failures. | Automated | Pending | API automation report
REQ-PERF-001 | UI performance baseline | UI | Performance / Smoke | Measure response time and request failure rate for the application entry point. | Automated | Passed | k6 ui-smoke.js: p95 77.77 ms; failure rate 0%.
REQ-PERF-002 | UI load performance | UI | Performance / Load | Measure response time, throughput and error rate under expected concurrent traffic. | Automated | Pending | k6 ui-load.js
REQ-PERF-003 | UI stress performance | UI | Performance / Stress | Increase load progressively to identify performance degradation/failure point. | Automated | Pending | k6 stress test report
REQ-PERF-004 | UI soak performance | UI | Performance / Soak | Maintain sustained traffic to identify long-duration degradation or resource issues. | Automated | Pending | k6 soak test report
REQ-PERF-005 | UI spike performance | UI | Performance / Spike | Apply sudden traffic increase and observe recovery/stability. | Automated | Pending | k6 spike test report
REQ-PERF-006 | API performance baseline | API | Performance / Smoke | Measure API response time and failure rate for a representative endpoint. | Automated | Pending | k6 API smoke test
REQ-PERF-007 | API load performance | API | Performance / Load | Measure API latency, throughput and error rate under expected concurrent traffic. | Automated | Pending | k6 API load test
REQ-PERF-008 | API stress performance | API | Performance / Stress | Determine behavior as concurrent API traffic increases beyond expected load. | Automated | Pending | k6 API stress test

## Status Legend
TRACEABILITY MATRIX – STATUS LEGEND
Status | Meaning | Recommended Action
Passed | Requirement/test coverage executed successfully. | Retain evidence/report.
Failed | Test executed but expected result was not met. | Log defect and retest after fix.
Pending | Test is defined but execution is not completed. | Execute when environment/data is ready.
Blocked – data | Execution is blocked by missing/insufficient test data or environment dependency. | Prepare data/dependency, then execute.
Not Executed | No execution has been performed yet. | Schedule execution.

## Document Control
DOCUMENT CONTROL
Document Name | Traceability Matrix
Project | Practice Software Testing
Document Type | QA / SQA Test Management Artifact
Version | 1.0
Status | Ready for project execution tracking
Owner | QA / SQA
Last Updated | 2026-08-07